## Estimation_Technology_Date
Shopping List
Time is estmate for a senior to do the work and fully unit test
Screen / Feature Name(s) | Feature Name | Priority | Best Case | Most Likely | Worst Case | Projections / Actuals | P/A | Notes | P1 B | P1 M | P1 W | P1 A | P2 B | P2 M | P2 W | P2 A
Documentation | Technical Design Document | 1 | 10 | 16 | 24 |  |  | Create, Review, Release TDD, Maintain | 10 | 16 | 24 |  | 0 | 0 | 0
Project Setup | Setup | 1 | 4 | 6 | 8 |  |  | Create new git repo, establish .gitignore, establish blank project, commit, branch, team clone. | 4 | 6 | 8 |  | 0 | 0 | 0
Data Model - Shopping List | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 |  | 0 | 0 | 0
Data Model - Shopping List Item | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 |  | 0 | 0 | 0
Data Model - Note | Data Model | 1 | 4 | 6 | 8 |  |  | Create data model as specified in TDD | 4 | 6 | 8 |  | 0 | 0 | 0
Add new items | Adding Items | 2 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Persist items to database | Items to database | 2 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Check off items | Check off items | 2 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Clear items | Clear items | 2 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Ordering of items | Ordering of items | 3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Sorting of items | Sorting of items | 3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Delete Indivdual items | Delete items | 3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Edit Items | Edit items | 3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Add notes to items | Add notes | 3 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Multiple User | Multiple users | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Login and Auth | Login | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Grouping of lists | Grouping of lists | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
List Template | List Template | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Web API | API | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Developer portal | Dev portal | 4 | [6 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Deployment | Deploy | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Apply Design Template | Design | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0
Testing | Test | [6 empty] | Author test plan, test cases, log bugs | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Priority | Best Case | Most Likely | Worst Case | Projected / Actuals
TOTAL HOURS - DEVELOPMENT ONLY |  | All | 16 | 24 | 32 | 0 | P/A
Priority 1 Only |  | 1 | 16 | 24 | 32 | 0 | P/A |  | 16 | 24 | 32 | 0 | 0 | 0 | 0 | 0
Priority 2 Only |  | 2 | 0 | 0 | 0 | 0 | P/A
TOTAL HOURS WITH RESOURCES - ALL | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 5.44 | 8.16 | 10.88
Apprentice 2 | 100% | 33% | 5.28 | 7.92 | 10.56
Apprentice 3 | 100% | 33% | 5.28 | 7.92 | 10.56
100%
PM |  | 20% | 3.2 | 4.8 | 6.4
Test |  | 20% | 3.2 | 4.8 | 6.4
TOTAL HOURS WITH RESOURCES- P1 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 5.44 | 8.16 | 10.88
Apprentice 2 | 100% | 33% | 5.28 | 7.92 | 10.56
Apprentice 3 | 100% | 33% | 5.28 | 7.92 | 10.56
100%
PM |  | 20% | 3.2 | 4.8 | 6.4
Test |  | 20% | 3.2 | 4.8 | 6.4
TOTAL HOURS WITH RESOURCES - P2 Only | Resource Weights | % Project | Best Case | Most Likely | Worst Case
Apprentice 1 | 100% | 34% | 0 | 0 | 0
Apprentice 2 | 100% | 33% | 0 | 0 | 0
Apprentice 3 | 100% | 33% | 0 | 0 | 0
100%
PM |  | 20% | 0 | 0 | 0
Test |  | 20% | 0 | 0 | 0

## Libraries
Library Name | Priority | Notes

## Images
Images Needed
Screen | Image | Notes

## Version History
Version | Date | Author | Notes
1 |  |  | Initial Draft
2
3
4
5
6

## References
Reference Name | Location | Filename / Notes